## AFI equipments
N° | Shop | Customer Name | MCO | Customer order | WO | PN | SN | Designation | Remarks | Qty | Start Date | Request Delivery Date / Plan ( * ) | Expected Delivery Date | Status COMP | Quote Asked ? | WO Status Quote | Total Quotation (Q3) | Contractual Time Limit | Repair TAT | Nb Planned Hours WO | Nb Badged Hours | Tech | CAPA | Has Changed
26. | D150 | AIR FRANCE INDUSTRIES | 5000320956 | 9L148498BVR | 3031711 | 49-170-07 | 1122 | SLAT AND FLAP CONTROL COMPUTER | pending AFI to advise on the repair short of details for qt, cover repaired by Tay pending PP information 13 feb | 1 | 12/12/19 | 20/12/19 | 20/12/19 | 10 | NO | Q1 |  | 74 | 82. | 9.50 | 16.84 |  | C
36. | D120 | AIR FRANCE INDUSTRIES | 5000322947 | 0A165948BXR | 3038914 | TAAI1-03CE01-02 | R356 | CO-PILOT SEAT | QUOTED 25 FEB, might be BER stop work | 1 | 16/01/20 | 24/01/20 | 24/01/20 | 10 | YES | Q3 | 26041 | 39 | 47. | 15.00 | 18.28 |  | C
43. | D150 | AIR FRANCE INDUSTRIES | 5000323226 | 0A170828X5R | 3040022 | 8055515-4501 | PTA45B-11903 | PRINTER | quoted 05 feb, unit from France Team | 1 | 21/01/20 | 03/02/20 | 03/02/20 | 90 | YES | Q3 | 1823 | 29 | 42. | 7.50 | 4.36 |  | A
66. | D150 | AIR FRANCE INDUSTRIES | 5000323777 | 0A234338BPR | 3041236 | 350E053021818 | 0E0006072 | FLIGHT WARNING COMPUTER | subcon to airbus, quoted 28 feb | 1 | 29/01/20 | 18/02/20 | 18/02/20 | 10 | NO | Q3 | 7169 | 14 | 34. | 0.00 | 1.62 |  | C
67. | D150 | AIR FRANCE INDUSTRIES | 5000324554 | 0B110668BVR | 3044313 | 49-170-11 | 49-170BA05547 | SLAT AND FLAP CONTROL COMPUTER | warranty unit | 1 | 10/02/20 | 20/02/20 | 20/02/20 | 10 | YES |  |  | 12 | 22. | 7.50 | 2.18 |  | A
68. | D150 | AIR FRANCE INDUSTRIES | 5000324579 | 0B126178BXR | 3044338 | 49-170-11 | 05063 | SLAT AND FLAP CONTROL COMPUTER |  | 1 | 10/02/20 | 20/02/20 | 20/02/20 | 10 | YES |  |  | 12 | 22. | 9.50 | 4.52 |  | C
70. | D120 | AIR FRANCE INDUSTRIES | 5000325156 | 0B177938BVR | 3046158 | TAAI3-03PE20-01 | 1350 | PILOT SEAT | APPROVED 03 MAR, EDD 17 APR 4136290006R ACTUATOR | 1 | 19/02/20 | 21/02/20 | 21/02/20 | 60 | YES | Q3 | 16808 | 11 | 13. | 15.00 | 20.79 |  | C | Yes
82. | D200 | AIR FRANCE INDUSTRIES | 5000324991 | 0B160798BPR | 3045448 | 1303A0000-04 | 02082 | FLOW CONTROL VALVE | short of information to quote, 3rd unit fairly new | 1 | 17/02/20 | 27/02/20 | 27/02/20 | 10 | NO | Q1 |  | 5 | 15. | 12.00 | 5.78 |  | C
83. | D060 | AIR FRANCE INDUSTRIES | 5000325093 | 0B177378BXR | 3045879 | 753C0000-02 | 05007 | EXCHANGER HEAT PRIMARY | APPROVED 03 MAR, EDD 06 MAR | 1 | 18/02/20 | 28/02/20 | 28/02/20 | 90 | YES | Q3 | 974 | 4 | 14. | 0.00 | 6.53 |  | C | Yes
84. | D060 | AIR FRANCE INDUSTRIES | 5000325095 | 0B178778BPR | 3045875 | VFT300B00 | 2272 | SKIN AIR VALVE | warranty unit, approved 03 mar, edd 11 mar | 1 | 18/02/20 | 28/02/20 | 28/02/20 | 90 | YES | Q3 | 2312 | 4 | 14. | 7.50 | 5.08 |  | A | Yes
85. | D060 | AIR FRANCE INDUSTRIES | 5000325098 | 0B177388BXR | 3045880 | 754C0000-01 | 81212-61263 | MAIN HEAT EXCHANGER |  | 1 | 18/02/20 | 28/02/20 | 28/02/20 | 10 | YES |  |  | 4 | 14. | 0.00 | 12.09 |  | C
86. | D060 | AIR FRANCE INDUSTRIES | 5000325099 | 0B177348BXR | 3045881 | 754C0000-01 | 81212-61553 | MAIN HEAT EXCHANGER |  | 1 | 18/02/20 | 28/02/20 | 28/02/20 | 10 | YES |  |  | 4 | 14. | 0.00 | 4.31 |  | C
87. | D060 | AIR FRANCE INDUSTRIES | 5000325237 | 0B186408BXR | 3046313 | 755D0000-01 | 81210-51291 | REHEATER |  | 1 | 20/02/20 | 28/02/20 | 28/02/20 | 10 | YES |  |  | 4 | 12. | 0.00 | 2.12 |  | C
88. | D060 | AIR FRANCE INDUSTRIES | 5000325340 | 0B195768BPR | 3046779 | 756A0000-05 | 01104 | CONDENSER | APPROVED 03 MAR, EDD 06 MAR | 1 | 21/02/20 | 28/02/20 | 28/02/20 | 10 | YES | Q3 | 996 | 4 | 11. | 0.00 | 8.49 |  | C | Yes
91. | D150 | AIR FRANCE INDUSTRIES | 5000325097 | 0B177738BVR | 3045878 | 215TS07Y00 | 5870 | L/G CONTROL LEVER | QUOTED 26 FEB | 1 | 18/02/20 | 28/02/20 | 28/02/20 | 10 | YES | Q3 | 454 | 4 | 14. | 7.50 | 2.50 |  | A
101. | D150 | AIR FRANCE INDUSTRIES | 5000325409 | 0B204118BQR | 3047355 | ACP2788AD01 | 2788-30552 | AUDIO CONTROL PANEL | approved 03 mar, edd tba 4136AB04R PUSH BUTTON | 1 | 24/02/20 | 02/03/20 | 02/03/20 | 60 | YES | Q3 | 1785 | 1 | 8. | 7.50 | 1.92 |  | A | Yes
103. | D060 | AIR FRANCE INDUSTRIES | 5000322722 | 0A147048BVR | 3038325 | HTE190001-2 | 493GB240 | ACTUATOR | edd: 28 feb, maybe be able to completed today after 3pm confirm again. | 1 | 14/01/20 | 03/03/20 | 03/03/20 | 90 | NO | Q7 |  | 0 | 49. | 0.00 | 31.38 |  | C
104. | D060 | AIR FRANCE INDUSTRIES | 5000324987 | 0B169148BXR | 3045444 | EVT3454HC | 164908309 | FAN | approved 26 feb, edd 3 mar | 1 | 17/02/20 | 03/03/20 | 03/03/20 | 90 | NO | Q3 | 2900 | 0 | 15. | 13.00 | 9.35 |  | C
105. | D060 | AIR FRANCE INDUSTRIES | 5000324988 | 0B169238BVR | 3045445 | VFT300B00 | 042604282 | SKIN AIR VALVE | EDD: 2 MAR | 1 | 17/02/20 | 03/03/20 | 03/03/20 | 90 | NO | Q7 |  | 0 | 15. | 10.00 | 9.78 |  | C
106. | D060 | AIR FRANCE INDUSTRIES | 5000325511 | 0B219008BPR | 3047523 | 754D0000-01 | 81212-69192 | MAIN EXCHANGER |  | 1 | 25/02/20 | 03/03/20 | 03/03/20 | 10 | NO |  |  | 0 | 7. | 3.00 | 11.94 |  | C
107. | D060 | AIR FRANCE INDUSTRIES | 5000325516 | 0B218988BPR | 3047528 | 754D0000-01 | 81212-69109 | MAIN EXCHANGER |  | 1 | 25/02/20 | 03/03/20 | 03/03/20 | 90 | NO |  |  | 0 | 7. | 3.00 | 9.72 |  | C
108. | D060 | AIR FRANCE INDUSTRIES | 5000325632 | 0B226868BQR | 3047731 | VFT210B00 | 042705550 | VALVE SKIN AIR |  | 1 | 27/02/20 | 03/03/20 | 03/03/20 | 10 | YES |  |  | 0 | 5. | 7.50 |  |  | A | Yes
113. | D065 | AIR FRANCE INDUSTRIES | 5000324574 | 0B121468BXR | 3044333 | MF20-534 | SE26755 | FULL FACE QUICK DONNING MASK | approved 19 feb, edd: 28 feb 422B340 OVH KIT MASK REGULATOR | 1 | 10/02/20 | 03/03/20 | 03/03/20 | 90 | NO | Q7 | 2980 | 0 | 22. | 4.00 | 5.47 |  | C | Yes
114. | D150 | AIR FRANCE INDUSTRIES | 5000317377 | 9J176808BVR | 3022572 | SIC5059-13-10 | AS0880 | FQIS FUEL QUANTITY INDICATION | approved 06 jan, edd 10 mar SIC8602-3R ASSY PSU BOARD | 1 | 16/10/19 | 03/03/20 | 03/03/20 | 60 | NO | Q7 | 10000 | 0 | 139. | 11.00 | 5.98 |  | C
123. | D060 | AIR FRANCE INDUSTRIES | 5000322849 | 0A155768BWR | 3038611 | 14330-375 | 3530 | GENERATOR-VACUUM | approved 17 feb - edd: 6 mar | 1 | 15/01/20 | 04/03/20 | 04/03/20 | 90 | NO | Q7 | 10985 | -1 | 48. | 11.00 | 5.92 |  | C | Yes
124. | D060 | AIR FRANCE INDUSTRIES | 5000323545 | 0A219708BQR | 3040646 | HTE200002-1 | 12090181 | ACTUATOR | approved 07 feb, edd: 4 mar | 1 | 24/01/20 | 04/03/20 | 04/03/20 | 90 | NO | Q7 | 778 | -1 | 39. | 0.00 | 11.20 |  | C | Yes
125. | D060 | AIR FRANCE INDUSTRIES | 5000323805 | 0A226508BXR | 3041263 | 322200-7M00 | AC03702 | NOSE STEERING HANDWHEEL | approved 20 feb, EDD: 3 MAR 322214 COVER | 1 | 29/01/20 | 04/03/20 | 04/03/20 | 90 | NO | Q7 | 2391 | -1 | 34. | 7.00 | 2.20 |  | C
126. | D060 | AIR FRANCE INDUSTRIES | 5000325573 | 0B219098BQR | 3047646 | 756A0000-06 | 841210-50995 | CONDENSER |  | 1 | 26/02/20 | 04/03/20 | 04/03/20 | 10 | NO |  |  | -1 | 6. | 0.00 | 2.72 |  | C
132. | D150 | AIR FRANCE INDUSTRIES | 5000325635 | 0B226738BQR | 3047734 | 89-01-07035 | 186622 | HANDSET | APPROVED 02 MAR, EDD 04 MAR | 1 | 27/02/20 | 04/03/20 | 04/03/20 | 10 | NO | Q7 | 168 | -1 | 5. | 7.50 | 0.94 |  | A
135. | D200 | AIR FRANCE INDUSTRIES | 5000322852 | 0A155618BXR | 3038614 | 1312B0000-01 | EX-2097 | BYPASS-VALVE | QUOTED 26 FEB, serial number should be 1312B00LI001060 | 1 | 20/02/20 | 04/03/20 | 04/03/20 | 90 | NO | Q7 | 2957 | -1 | 12. | 0.00 | 14.57 |  | C | Yes
136. | D060 | AIR FRANCE INDUSTRIES | 5000323897 | 0A254968BQR | 3041414 | 796-809-6A | 17533 | CADENSICON | approved 07 feb, edd: 05 march WAX3ZZT6H20K71 BEARING BALL ANNULAR | 1 | 30/01/20 | 05/03/20 | 05/03/20 | 70 | NO | Q7 | 3121 | -2 | 33. | 7.50 | 10.15 |  | A
137. | D060 | AIR FRANCE INDUSTRIES | 5000325158 | 0B186598BPR | 3046159 | VFT210A2 | 2619 | VALVE-SKIN AIR | EDD: 5 MAR | 1 | 19/02/20 | 05/03/20 | 05/03/20 | 90 | YES | Q7 |  | -2 | 13. | 25.00 | 4.45 |  | C | Yes
138. | D060 | AIR FRANCE INDUSTRIES | 5000325630 | 0B226748BQR | 3047729 | J540AI4-100 | 09114200 | VACUUM GENERATOR ASSEMBLY |  | 1 | 27/02/20 | 05/03/20 | 05/03/20 | 10 | YES | Q2 |  | -2 | 5. | 6.00 | 3.95 |  | C
139. | D150 | AIR FRANCE INDUSTRIES | 5000321789 | 9L218168BPR | 3034092 | SIC5059-14-31 | FE001311 | FQIS FUEL QUANTITY INDICATION | on 20 feb, still not subcon AA unit, Customer, finished testing but not sure whether we able to repair. PP confirm to subcon to ontic 14 feb, received on 26 feb at ontic | 1 | 26/12/19 | 05/03/20 | 05/03/20 | 10 | YES | Q2 |  | -2 | 68. | 11.00 | 10.41 |  | C
140. | D150 | AIR FRANCE INDUSTRIES | 5000325422 | 0B211358BPR | 3047366 | LA2T0G20705C070 | 2T0008614 | ATSU | EDD: 5 MAR | 1 | 24/02/20 | 05/03/20 | 05/03/20 | 90 | YES | Q7 |  | -2 | 8. | 0.00 | 2.10 |  | C | Yes
141. | D150 | AIR FRANCE INDUSTRIES | 5000325627 | 0B207388MDR | 3047726 | ACP2788AB05 | 2788-16818 | AUDIO CONTROL PANEL |  | 1 | 27/02/20 | 05/03/20 | 05/03/20 | 10 | YES |  |  | -2 | 5. | 7.50 | 1.99 |  | A
142. | D150 | AIR FRANCE INDUSTRIES | 5000325628 | 0B208848IZR | 3047727 | 7000700-961 | 03019416 | AIR DATA COMPUTER |  | 1 | 27/02/20 | 05/03/20 | 05/03/20 | 10 | YES |  |  | -2 | 5. | 7.50 |  |  | A
143. | D150 | AIR FRANCE INDUSTRIES | 5000325634 | 0B229528BXR | 3047733 | 8055515-4501 | PTA45B-10417 | PRINTER |  | 1 | 27/02/20 | 05/03/20 | 05/03/20 | 10 | YES | Q2 |  | -2 | 5. | 7.50 | 0.85 |  | A
148. | D060 | AIR FRANCE INDUSTRIES | 5000322448 | 0A107208BPR | 3037564 | HTE190001-2 | 28155106 | ACTUATOR | edd: 6 MAR, MOTOR FAULTY --> edd will confirm again | 1 | 09/01/20 | 06/03/20 | 06/03/20 | 90 | NO | Q7 |  | -3 | 54. | 0.00 | 43.13 |  | C | Yes
149. | D060 | AIR FRANCE INDUSTRIES | 5000322828 | 0A157108BXR | 3038590 | VD3810 | 05022854 | FAN | edd: 15 feb, edd 28 feb --> 6 MAR 3810-0101-0000R HOUSING EQUIPE --> ship today | 1 | 15/01/20 | 06/03/20 | 06/03/20 | 90 | YES | Q7 |  | -3 | 48. | 10.00 | 4.46 |  | C
150. | D060 | AIR FRANCE INDUSTRIES | 5000324217 | 0A282718BVR | 3042809 | HTE190001-2 | 45126205 | ACTUATOR | edd: tba HTE2501A MOTOR MS29513-032 PACKING MS29513-019 SEAL | 1 | 04/02/20 | 06/03/20 | 06/03/20 | 60 | NO | Q7 |  | -3 | 28. | 0.00 | 4.75 |  | C
151. | D060 | AIR FRANCE INDUSTRIES | 5000325162 | 0B185678BPR | 3046164 | HTE200002-1 | 891GB222 | ACTUATOR | edd: 06 mar | 1 | 19/02/20 | 06/03/20 | 06/03/20 | 90 | NO | Q7 |  | -3 | 13. | 0.00 | 3.86 |  | C
152. | D060 | AIR FRANCE INDUSTRIES | 5000325345 | 0B205508BPR | 3046780 | 796-809-6A | 14781 | CADENSICON | approved 25 feb, edd: tba | 1 | 21/02/20 | 06/03/20 | 06/03/20 | 60 | NO | Q7 | 3245 | -3 | 11. | 14.20 | 9.51 |  | C
153. | D060 | AIR FRANCE INDUSTRIES | 5000325346 | 0B205218BPR | 3046781 | AE1502U02 | 152304111 | MOTOR BRAKE COOLING FAN | quoted 02 mar | 1 | 21/02/20 | 06/03/20 | 06/03/20 | 10 | NO | Q3 | 8719 | -3 | 11. | 5.00 | 4.36 |  | C | Yes
154. | D060 | AIR FRANCE INDUSTRIES | 5000325415 | 0B196538BQR | 3047361 | HTE200002-1 | 16196202 | ACTUATOR | EDD: 7 MAR | 1 | 24/02/20 | 06/03/20 | 06/03/20 | 90 | NO | Q7 |  | -3 | 8. | 0.00 | 4.42 |  | C
155. | D060 | AIR FRANCE INDUSTRIES | 5000325428 | 0B211528BPR | 3047530 | EVT3454HC | 164908571 | FAN | approved 28 feb, 6mar | 1 | 25/02/20 | 06/03/20 | 06/03/20 | 90 | YES | Q7 |  | -3 | 7. | 16.00 | 2.58 |  | C
156. | D060 | AIR FRANCE INDUSTRIES | 5000325509 | 0B219728BQR | 3047521 | EVT3454HC | 05760 | FAN | EDD: 06 MAR | 1 | 25/02/20 | 06/03/20 | 06/03/20 | 90 | NO | Q7 |  | -3 | 7. | 13.00 | 5.54 |  | C
157. | D060 | AIR FRANCE INDUSTRIES | 5000325626 | 0B227018BPR | 3047725 | 756B0000-01 | 841210-67011 | CONDENSER |  | 1 | 27/02/20 | 06/03/20 | 06/03/20 | 10 | YES |  |  | -3 | 5. | 0.00 | 2.13 |  | C | Yes
158. | D060 | AIR FRANCE INDUSTRIES | 5000325629 | 0B226818BPR | 3047728 | 756B0000-01 | 841210-66857 | CONDENSER |  | 1 | 27/02/20 | 06/03/20 | 06/03/20 | 10 | YES |  |  | -3 | 5. | 0.00 |  |  | C | Yes
159. | D060 | AIR FRANCE INDUSTRIES | 5000325740 | 0B235058BXR | 3047950 | VFT300B00 | 042603050 | SKIN AIR VALVE |  | 1 | 28/02/20 | 06/03/20 | 06/03/20 | 10 | NO |  |  | -3 | 4. | 7.00 |  |  | C
160. | D060 | AIR FRANCE INDUSTRIES | 5000325744 | 0B235158BXR | 3047954 | 755C0000-01 | 81210-53673 | RH REHEATER |  | 1 | 28/02/20 | 06/03/20 | 06/03/20 | 10 | NO |  |  | -3 | 4. | 5.00 |  |  | C
161. | D060 | AIR FRANCE INDUSTRIES | 5000325756 | 0B235208BPR | 3047966 | 756A0000-06 | 841210-50340 | CONDENSER |  | 1 | 28/02/20 | 06/03/20 | 06/03/20 | 10 | YES |  |  | -3 | 4. | 0.00 |  |  | C | Yes
167. | D065 | AIR FRANCE INDUSTRIES | 5000325750 | 0B235078BXR | 3047961 | MF20-534 | SE73734 | FULL FACE QUICK DONNING MASK |  | 1 | 28/02/20 | 06/03/20 | 06/03/20 | 10 | YES |  |  | -3 | 4. | 4.00 |  |  | C
169. | D150 | AIR FRANCE INDUSTRIES | 5000314518 | 9H213538BQR | 3014591 | 785002-9 | 785002IN7625 | BLEED MONITORING COMPUTER BMC | EDD: 14 feb --> having trouble repair, delay to 1st week march EDD: 6 mar | 1 | 28/08/19 | 06/03/20 | 06/03/20 | 90 | YES | Q7 |  | -3 | 188. | 0.00 | 20.78 |  | C
170. | D150 | AIR FRANCE INDUSTRIES | 5000316522 | 9I259448BQR | 3020003 | 49-170-11 | 49-170BA05506 | SLAT AND FLAP CONTROL COMPUTER | approved 21 oct, Tay checking 11 Feb | 1 | 01/10/19 | 06/03/20 | 06/03/20 | 90 | NO | Q7 | 818 | -3 | 154. | 9.50 | 10.66 |  | C
171. | D150 | AIR FRANCE INDUSTRIES | 5000321740 | 9L211198BPR | 3033987 | E21327007 | 2699 | BRAKING AND STEERING CONTROL U | APPROVED 20 JAN, edd: tba pending TAY | 1 | 24/12/19 | 06/03/20 | 06/03/20 | 90 | NO | Q7 | 8605 | -3 | 70. | 15.50 | 15.11 |  | C
172. | D150 | AIR FRANCE INDUSTRIES | 5000322057 | 9L226558BPR | 3035680 | ACP2788AF01 | 882 | AUDIO CONTROL PANEL | approved 17 jan, mod kit edd end feb, delay to 6 mar | 1 | 02/01/20 | 06/03/20 | 06/03/20 | 60 | NO | Q7 | 2219 | -3 | 61. | 4.00 | 6.26 |  | B
173. | D150 | AIR FRANCE INDUSTRIES | 5000323786 | 0A226608BPR | 3043845 | E21327007 | 00298 | BRAKING AND STEERING CONTROL U | edd: 21 feb, delay to | 1 | 07/02/20 | 06/03/20 | 06/03/20 | 90 | NO | Q7 |  | -3 | 25. | 15.50 | 32.84 |  | C
174. | D150 | AIR FRANCE INDUSTRIES | 5000324310 | 0B100258BXR | 3043001 | E21327106 | 10374 | BRAKING AND STEERING CONTROL U | edd: 24 feb --> 21 feb | 1 | 05/02/20 | 06/03/20 | 06/03/20 | 90 | NO | Q7 |  | -3 | 27. | 15.50 | 13.58 |  | C
175. | D150 | AIR FRANCE INDUSTRIES | 5000325642 | 0B226768BQR | 3047741 | N40-1B20212-102 | 271AF18066 | HANDSET WITH SUPPORT BRACKET |  | 1 | 27/02/20 | 06/03/20 | 06/03/20 | 10 | YES |  |  | -3 | 5. | 7.50 | 1.17 |  | A
176. | D150 | AIR FRANCE INDUSTRIES | 5000325743 | 0B235048BQR | 3047953 | N40-1B20203-102 | 305942 | HANDSET WITH SUPPORT BRACKET |  | 1 | 28/02/20 | 06/03/20 | 06/03/20 | 10 | YES |  |  | -3 | 4. | 7.50 |  |  | A
177. | D150 | AIR FRANCE INDUSTRIES | 5000325818 | 0B244038BXR | 3048206 | N40-1B20212-102 | 425415 | HANDSET WITH SUPPORT BRACKET |  | 1 | 02/03/20 | 06/03/20 | 06/03/20 | 10 | YES |  |  | -3 | 1. | 7.50 |  |  | A
186. | D200 | AIR FRANCE INDUSTRIES | 5000323889 | 0A252708BQR | 3041403 | 1303A0000-04 | 00849 | FLOW CONTROL VALVE | approved 11 feb, edd 6 mar 22224CM050010 SCREW 22256CM030010 SCREW 6723-01710 BODY 6733-15 SHIM S3348-05 SHIM S3348-2 WASHER | 1 | 30/01/20 | 06/03/20 | 06/03/20 | 60 | NO | Q7 | 7544 | -3 | 33. | 12.00 | 10.30 |  | C
187. | D200 | AIR FRANCE INDUSTRIES | 5000325640 | 0B226828BQR | 3047739 | 1394A0000-01 | 1394-02371 | TEMPERATURE CONTROL VALVE |  | 1 | 27/02/20 | 06/03/20 | 06/03/20 | 10 | NO |  |  | -3 | 5. | 22.00 | 2.06 |  | C | Yes
191. | D060 | AIR FRANCE INDUSTRIES | 5000325736 | 0B235138BQR | 3047946 | AE1502U02 | 08357 | MOTOR BRAKE COOLING FAN |  | 1 | 28/02/20 | 09/03/20 | 09/03/20 | 10 | NO |  |  | -6 | 4. | 5.00 |  |  | C
192. | D060 | AIR FRANCE INDUSTRIES | 5000325738 | 0B235118BQR | 3047948 | EVT3454HC | 2223 | FAN |  | 1 | 28/02/20 | 09/03/20 | 09/03/20 | 10 | NO |  |  | -6 | 4. | 13.00 |  |  | C
193. | D060 | AIR FRANCE INDUSTRIES | 5000325837 | 0B251918BVR | 3048226 | VFT210B00 | 042703667 | VALVE SKIN AIR |  | 1 | 02/03/20 | 09/03/20 | 09/03/20 | 10 | NO |  |  | -6 | 1. | 25.00 |  |  | C
194. | D060 | AIR FRANCE INDUSTRIES | 5000325853 | 0B260708BPR | 3048246 | VFT210B00 | 042705094 | VALVE SKIN AIR |  | 1 | 02/03/20 | 09/03/20 | 09/03/20 | 10 | YES |  |  | -6 | 1. | 7.50 |  |  | A
195. | D060 | AIR FRANCE INDUSTRIES | 5000325878 | 0B260908BPR | 3048271 | VFT300B00 | 042605679 | SKIN AIR VALVE |  | 1 | 02/03/20 | 09/03/20 | 09/03/20 | 10 | NO |  |  | -6 | 1. | 10.00 |  |  | C
196. | D060 | AIR FRANCE INDUSTRIES | 5000325880 | 0B261938BVR | 3048272 | VFT300B00 | 042600411 | SKIN AIR VALVE |  | 1 | 02/03/20 | 09/03/20 | 09/03/20 | 10 | YES |  |  | -6 | 1. | 7.50 |  |  | A
198. | D150 | AIR FRANCE INDUSTRIES | 5000325741 | 0B236708BQR | 3047951 | 35-0L0-1001-04 | 0L0001379 | ECAM CONTROL PANEL | edd: 11 mar | 1 | 28/02/20 | 09/03/20 | 09/03/20 | 10 | NO | Q2 |  | -6 | 4. | 5.00 |  |  | C | Yes
199. | D150 | AIR FRANCE INDUSTRIES | 5000325839 | 0C100538BQR | 3048228 | E21327007 | 1349 | BRAKING AND STEERING CONTROL U |  | 1 | 02/03/20 | 09/03/20 | 09/03/20 | 10 | NO |  |  | -6 | 1. | 6.00 |  |  | C
200. | D150 | AIR FRANCE INDUSTRIES | 5000325851 | 0B259938BQR | 3048244 | APE5100-1 | 2870 | ELECTRONIC CLOCK |  | 1 | 02/03/20 | 09/03/20 | 09/03/20 | 10 | NO |  |  | -6 | 1. | 3.00 |  |  | C | Yes
201. | D150 | AIR FRANCE INDUSTRIES | 5000325875 | 0B260668BQR | 3048270 | N40-1B20203-102 | 377959 | HANDSET WITH SUPPORT BRACKET |  | 1 | 02/03/20 | 09/03/20 | 09/03/20 | 10 | YES |  |  | -6 | 1. | 7.50 | 0.61 |  | A | Yes
202. | D150 | AIR FRANCE INDUSTRIES | 5000325881 | 0B260578BXR | 3048274 | SIC5059-14-20 | AS2111 | COMPUTER FUEL QUANTITY IND |  | 1 | 02/03/20 | 09/03/20 | 09/03/20 | 10 | NO |  |  | -6 | 1. | 11.00 |  |  | C | Yes
205. | D200 | AIR FRANCE INDUSTRIES | 5000325857 | 0B260848BQR | 3048268 | 6740F010000 | 6740-07837 | OVERPRESSURE VALVE | unit failed incoming test, checking whether to proceed | 1 | 02/03/20 | 09/03/20 | 09/03/20 | 10 | NO |  |  | -6 | 1. | 12.00 | 1.71 |  | C | Yes
208. | D060 | AIR FRANCE INDUSTRIES | 5000325637 | 0B227058BQR | 3047736 | AR4714-11 | 1018882 | STRIKE | approved 02 mar, edd 10 mar | 1 | 27/02/20 | 10/03/20 | 10/03/20 | 90 | NO | Q7 | 2704 | -7 | 5. | 4.00 | 1.96 |  | C
210. | D065 | AIR FRANCE INDUSTRIES | 5000325085 | 0B177318BPR | 3045867 | MF10-05-11 | 60875 | MASK-FULL FACE QUICK DONN | APPROVED 24 FEB, EDD: TBA 422B340 OVH KIT MASK REGULATOR | 1 | 18/02/20 | 10/03/20 | 10/03/20 | 90 | NO | Q7 | 2697 | -7 | 14. | 4.00 | 2.40 |  | C
213. | D150 | AIR FRANCE INDUSTRIES | 5000320592 | 9L125548BVR | 3030901 | E21327107 | 4946 | BSCU BRAKING STEERING CONTROL | edd: 10 mar | 1 | 09/12/19 | 10/03/20 | 10/03/20 | 10 | NO | Q7 |  | -7 | 85. | 15.50 | 27.71 |  | C
222. | D060 | AIR FRANCE INDUSTRIES | 5000325830 | 0B251608BXR | 3048218 | 756A0000-06 | 841210-50642 | CONDENSER |  | 1 | 02/03/20 | 12/03/20 | 12/03/20 | 10 | NO |  |  | -9 | 1. | 0.00 |  |  | C | Yes
223. | D060 | AIR FRANCE INDUSTRIES | 5000325831 | 0B251518BXR | 3048219 | EVT3454HC | 05805 | FAN |  | 1 | 02/03/20 | 12/03/20 | 12/03/20 | 10 | YES |  |  | -9 | 1. | 7.50 |  |  | A
227. | D150 | AIR FRANCE INDUSTRIES | 5000325819 | 0B251598BQR | 3048207 | N40-1B20212-102 | 404712 | HANDSET WITH SUPPORT BRACKET |  | 1 | 02/03/20 | 12/03/20 | 12/03/20 | 10 | NO | Q2 |  | -9 | 1. | 3.00 | 1.20 |  | C
228. | D150 | AIR FRANCE INDUSTRIES | 5000325821 | 0B244068BPR | 3048209 | 350E5500205 | 0E5010415 | SDAC SYSTEM DATA ACQUI CONCENT | edd: 10 mar | 1 | 02/03/20 | 12/03/20 | 12/03/20 | 10 | NO | Q2 |  | -9 | 1. | 4.00 | 4.74 |  | C | Yes
229. | D150 | AIR FRANCE INDUSTRIES | 5000325825 | 0B243988BQR | 3048213 | ACP2788AF01 | 2788-17589 | AUDIO CONTROL PANEL | EDD: 11 MAR | 1 | 02/03/20 | 12/03/20 | 12/03/20 | 10 | NO |  |  | -9 | 1. | 4.00 |  |  | B | Yes
230. | D150 | AIR FRANCE INDUSTRIES | 5000325827 | 0B243998BXR | 3048215 | N40-1B20212-102 | 363433 | HANDSET WITH SUPPORT BRACKET | edd: 10 mar | 1 | 02/03/20 | 12/03/20 | 12/03/20 | 10 | NO | Q2 |  | -9 | 1. | 3.00 | 0.87 |  | C | Yes
231. | D150 | AIR FRANCE INDUSTRIES | 5000325828 | 0B251778BQR | 3048216 | N40-1B10100-101 | 480428 | HANDSET WITH SUPPORT BRACKET | edd : TBA 27-14-90384 HOUSING BACK PART ASSY | 1 | 02/03/20 | 12/03/20 | 12/03/20 | 10 | NO | Q2 |  | -9 | 1. | 3.00 | 1.52 |  | C | Yes
235. | D060 | AIR FRANCE INDUSTRIES | 5000325631 | 0B227108BPR | 3047730 | VD3900-03 | 16078952 | RH FAN | quoted 03 mar | 1 | 27/02/20 | 13/03/20 | 13/03/20 | 10 | NO |  |  | -10 | 5. | 8.00 |  |  | C | Yes
236. | D060 | AIR FRANCE INDUSTRIES | 5000325639 | 0B226858BPR | 3047738 | VFT300B00 | 42604101 | SKIN AIR VALVE | EDD: 11 MAR | 1 | 27/02/20 | 13/03/20 | 13/03/20 | 10 | NO |  |  | -10 | 5. | 7.00 |  |  | C | Yes
237. | D060 | AIR FRANCE INDUSTRIES | 5000325747 | 0B235168BXR | 3047957 | VFT300B00 | 042600275 | SKIN AIR VALVE |  | 1 | 28/02/20 | 13/03/20 | 13/03/20 | 10 | NO |  |  | -10 | 4. | 7.00 |  |  | C
238. | D060 | AIR FRANCE INDUSTRIES | 5000325749 | 0B235098BQR | 3047959 | EVT3454HC | 164903377 | FAN |  | 1 | 28/02/20 | 13/03/20 | 13/03/20 | 10 | NO |  |  | -10 | 4. | 13.00 |  |  | C
244. | D150 | AIR FRANCE INDUSTRIES | 5000324558 | 0B118868BVR | 3044317 | 785002-9 | 785002IN7419 | BLEED MONITORING COMPUTER BMC | edd: 27 mar RB59-0U51J RESISTOR | 1 | 10/02/20 | 13/03/20 | 13/03/20 | 60 | NO | Q7 |  | -10 | 22. | 0.00 | 2.75 |  | C
245. | D150 | AIR FRANCE INDUSTRIES | 5000325096 | 0B179298BVR | 3045877 | ACP2788AD01 | 2788-23503 | AUDIO CONTROL PANEL | edd: 13 MAR 4136AB04R PUSH BUTTON 4206AA02100R EQUIPED FRONT PANEL | 1 | 18/02/20 | 13/03/20 | 13/03/20 | 60 | NO | Q7 |  | -10 | 14. | 5.00 | 1.56 |  | C
247. | D200 | AIR FRANCE INDUSTRIES | 5000325636 | 0B226728BQR | 3047735 | 1320A0000-02 | 1320A00LI002336 | VALVE-TRIM AIR |  | 1 | 27/02/20 | 13/03/20 | 13/03/20 | 10 | NO |  |  | -10 | 5. | 23.00 |  |  | C | Yes
251. | D060 | AIR FRANCE INDUSTRIES | 5000324226 | 0A282238BVR | 3042818 | 14330-375 | 1293 | GENERATOR-VACUUM | edd: 9 mar | 1 | 04/02/20 | 16/03/20 | 16/03/20 | 90 | NO | Q7 | 10070 | -13 | 28. | 11.00 | 5.36 |  | C
252. | D060 | AIR FRANCE INDUSTRIES | 5000324582 | 0B126168BXR | 3044341 | 14330-375 | 7901 | GENERATOR-VACUUM | approved 26 feb, edd: 10 MAR | 1 | 10/02/20 | 17/03/20 | 17/03/20 | 90 | NO | Q7 | 11150 | -14 | 22. | 11.00 | 5.00 |  | C
253. | D060 | AIR FRANCE INDUSTRIES | 5000325829 | 0B244128BQR | 3048217 | AR4714-11 | H-C9332 | STRIKE | quoted 03 mar | 1 | 02/03/20 | 17/03/20 | 17/03/20 | 10 | YES | Q2 |  | -14 | 1. | 4.00 | 1.50 |  | C | Yes
254. | D060 | AIR FRANCE INDUSTRIES | 5000325832 | 0B252218BQR | 3048220 | 796-809-6A | 16700 | CADENSICON |  | 1 | 02/03/20 | 17/03/20 | 17/03/20 | 10 | YES |  |  | -14 | 1. | 14.20 |  |  | C
256. | D200 | AIR FRANCE INDUSTRIES | 5000325820 | 0B251578BQR | 3048208 | 6740F010000 | 6740-07803 | OVERPRESSURE VALVE |  | 1 | 02/03/20 | 17/03/20 | 17/03/20 | 10 | NO | Q2 |  | -14 | 1. | 6.00 | 4.06 |  | C | Yes
257. | D200 | AIR FRANCE INDUSTRIES | 5000325822 | 0B244118BXR | 3048210 | 38E93-5 | 1753 | VALVE |  | 1 | 02/03/20 | 17/03/20 | 17/03/20 | 10 | YES |  |  | -14 | 1. | 15.00 | 0.93 |  | C | Yes
258. | D200 | AIR FRANCE INDUSTRIES | 5000325824 | 0B244098BQR | 3048212 | 1312B0000-01 | 1312-10331 | BYPASS-VALVE |  | 1 | 02/03/20 | 17/03/20 | 17/03/20 | 10 | NO |  |  | -14 | 1. | 0.00 |  |  | C | Yes
259. | D200 | AIR FRANCE INDUSTRIES | 5000325826 | 0B244108BQR | 3048214 | 38E93-5 | 1752 | VALVE |  | 1 | 02/03/20 | 17/03/20 | 17/03/20 | 10 | YES |  |  | -14 | 1. | 15.00 |  |  | C | Yes
262. | D060 | AIR FRANCE INDUSTRIES | 5000324550 | 0A279298BVR | 3044309 | VD3900-03 | 02670 | RH FAN | approved 24 feb, edd: 19 Mar 348309NP CONNECTOR ASSEMBLY | 1 | 10/02/20 | 19/03/20 | 19/03/20 | 60 | NO | Q7 | 2279 | -16 | 22. | 8.00 | 2.87 |  | C
263. | D060 | AIR FRANCE INDUSTRIES | 5000322218 | 9L251288BVR | 3046329 | 754D0000-01 | 81212-69136 | MAIN EXCHANGER | APPROVED 22 JAN, EDD 7 FEB, DELAY DUE TO NEW WELDING TOOL REQUIRED major repair, hydrati test pending liebherr | 1 | 20/02/20 | 20/03/20 | 20/03/20 | 10 | YES | Q7 |  | -17 | 12. | 5.00 |  |  | C
264. | D060 | AIR FRANCE INDUSTRIES | 5000322942 | 0A155678BWR | 3046330 | 754D0000-01 | 81212-66843 | MAIN EXCHANGER | major repair, hydrati test pending liebherr | 1 | 20/02/20 | 20/03/20 | 20/03/20 | 10 | YES | Q7 |  | -17 | 12. | 5.00 |  |  | C
266. | D150 | AIR FRANCE INDUSTRIES | 5000320802 | 9L140588BPR | 3031408 | SIC5059-14-31 | AS2208 | FQIS FUEL QUANTITY INDICATION | approved 26 dec, edd: 20 march T495X475M050AHE CAPACITOR | 1 | 11/12/19 | 20/03/20 | 20/03/20 | 60 | NO | Q7 | 954 | -17 | 83. | 11.00 | 11.84 |  | C
267. | D150 | AIR FRANCE INDUSTRIES | 5000325412 | 0B205078BXR | 3047358 | 785002-9 | 785002IN10205 | BLEED MONITORING COMPUTER BMC | edd: TBA LM108AH MICROCIRCUIT | 1 | 24/02/20 | 20/03/20 | 20/03/20 | 60 | NO | Q7 |  | -17 | 8. | 0.00 | 2.56 |  | C
273. | D060 | AIR FRANCE INDUSTRIES | 5000325084 | 0B169208BVR | 3045866 | VFT210B00 | 042702059 | VALVE SKIN AIR | edd: tba 8480-006 RING | 1 | 18/02/20 | 23/03/20 | 23/03/20 | 60 | NO | Q7 |  | -20 | 14. | 25.00 | 0.86 |  | C
277. | D060 | AIR FRANCE INDUSTRIES | 5000324571 | 0B120598BVR | 3044330 | HTE190001-2 | M645GB0100 | ACTUATOR | approved 25 feb, edd tba S006-062-0600 PIN TENSION | 1 | 10/02/20 | 25/03/20 | 25/03/20 | 60 | NO | Q7 | 1257 | -22 | 22. | 0.00 | 13.00 |  | C
282. | D150 | AIR FRANCE INDUSTRIES | 5000325638 | 0B226778BQR | 3047737 | N40-1B10100-101 | 383544 | HANDSET WITH SUPPORT BRACKET | EDD: TBA 27-14-90384 HOUSING BACK PART ASSY | 1 | 27/02/20 | 27/03/20 | 27/03/20 | 90 | NO | Q7 |  | -24 | 5. | 3.00 | 3.08 |  | C
283. | D150 | AIR FRANCE INDUSTRIES | 5000325733 | 0B235528BQR | 3047942 | N40-1B10100-101 | 466936 | HANDSET WITH SUPPORT BRACKET | edd: tba 27-14-90384 HOUSING BACK PART ASSY | 1 | 28/02/20 | 27/03/20 | 27/03/20 | 90 | NO | Q7 |  | -24 | 4. | 3.00 | 4.13 |  | C
284. | D060 | AIR FRANCE INDUSTRIES | 5000323887 | 0A252718BPR | 3041401 | 14330-350 | 07125532 | GENERATOR-VACUUM | approved 13 feb, PART SHORTAGE | 1 | 30/01/20 | 29/03/20 | 29/03/20 | 60 | NO | Q7 | 5562 | -26 | 33. | 11.00 | 4.63 |  | C
289. | D120 | AIR FRANCE INDUSTRIES | 5000322206 | 9L251368BPR | 3036150 | TAAI1-03CE01-02 | 368 | CO-PILOT SEAT | approved 17 feb, edd: 31 Mar 2510144290-60 LABEL 2510144290-61 LABEL TAAI1-408020-03 CUSHION, ASSY TAAI1-992111-02 PANEL, EQUIPPED | 1 | 06/01/20 | 31/03/20 | 31/03/20 | 60 | NO | Q7 | 8591 | -28 | 57. | 15.00 | 16.52 |  | C
293. | D060 | AIR FRANCE INDUSTRIES | 5000325823 | 0B244148BQR | 3048211 | AR4714-11 | H-D8052 | STRIKE | QUOTED 03 MAR | 1 | 02/03/20 | 02/04/20 | 02/04/20 | 10 | NO | Q3 | 3096 | -30 | 1. | 4.00 | 1.57 |  | C | Yes
295. | D200 | AIR FRANCE INDUSTRIES | 5000320385 | 9L100738BVR | 3030326 | 6740E010000 | 02071 | VALVE | approved 24 feb, edd | 1 | 04/12/19 | 03/04/20 | 03/04/20 | 60 | NO | Q7 | 4150 | -31 | 90. | 0.00 | 41.90 |  | C
301. | D120 | AIR FRANCE INDUSTRIES | 5000325160 | 0B185648BVR | 3046535 | TAAI1-03CE11-02 | 317 | SEAT POWERED FIRST OFFICER | APPROVED 26 FEB, EDD: TBA 4136290006R ACTUATOR | 1 | 20/02/20 | 10/04/20 | 10/04/20 | 60 | NO | Q7 | 8822 | -38 | 12. | 15.00 | 11.07 |  | C
302. | D150 | AIR FRANCE INDUSTRIES | 5000314246 | 9H193608BXR | 3013826 | 785002-9 | 1697 | BLEED MONITORING COMPUTER BMC | EDD: 10 apr P209473 RESISTOR 759 OHM SN74HC244N MICROCIRCUIT | 1 | 23/08/19 | 10/04/20 | 10/04/20 | 60 | YES | Q7 |  | -38 | 193. | 0.00 | 18.79 |  | C
303. | D150 | AIR FRANCE INDUSTRIES | 5000323109 | 0A183908BVR | 3039846 | SIC5059-14-20 | AS3030 | COMPUTER FUEL QUANTITY IND | urgent required, troubleshooting issue with soldering issue (ontic) tml subcon to ontic --> approved 02 mar, edd 13 apr | 1 | 20/01/20 | 11/04/20 | 11/04/20 | 10 | NO | Q7 | 6341 | -39 | 43. | 11.00 | 13.96 |  | C
304. | D120 | AIR FRANCE INDUSTRIES | 5000325339 | 0B204168BPR | 3046774 | TAAI3-03CE20-01 | A320-07182 | CO-PILOT SEAT | approved 28 feb | 1 | 21/02/20 | 13/04/20 | 13/04/20 | 60 | NO | Q7 | 11353 | -41 | 11. | 15.00 | 18.74 |  | C
312. | D060 | AIR FRANCE INDUSTRIES | 5000322533 | 0A129128BVR | 3037691 | 14330-375 | 541 | GENERATOR-VACUUM | APPROVED 6 FEB, EDD: 5 MAR | 1 | 10/01/20 | 03/05/20 | 03/05/20 | 90 | NO | Q7 | 13301 | -61 | 53. | 11.00 | 7.98 |  | C | Yes
313. | D060 | AIR FRANCE INDUSTRIES | 5000319664 | 9K193408BPR | 3028605 | 14330-375 | 3162 | GENERATOR-VACUUM | approved 29 jan, edd: 3 MAR | 1 | 22/11/19 | 10/05/20 | 10/05/20 | 60 | NO | Q7 | 16639 | -68 | 102. | 11.00 | 10.96 |  | C
314. | D060 | AIR FRANCE INDUSTRIES | 5000324556 | 0B118528BVR | 3044315 | 14330-375 | 2895 | GENERATOR-VACUUM | edd: tba S078941 SELF LOCKING NUT 28000-215 WASHER, SPECIAL 28000-100-1 BEARING, BALL 2805490-4 HOUSING ASSEMBLY 2805278-1 DIFFUSER PLATE 67410353-1R HOUSING ASSY SECOND_STAGE 2805489-4R HOUSING ASSY SCROLL | 1 | 10/02/20 | 10/05/20 | 10/05/20 | 60 | NO | Q7 |  | -68 | 22. | 11.00 | 5.39 |  | C